## use weeks not dates for the sta
Task | Responsible Role(s) | Start Week | End Week | Duration (Weeks) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Phase 1: Planning & Requirements
Project Proposal | Project Manager | 1 | 1 | 1 | bar: W1
Defining the domain | System Analyst | 1 | 2 | 1 | bar: W1 to W3
Project Plan | Project Manager/ All | 2 | 3 | 1 | bar: W2 to W3
SRS Document Draft | System Analyst | 4 | 5 | 2
Phase 2: Design
System and Database design | Software Architect | 6 | 7 | 1
User interface mockups | Developers | 6 | 8 | 2
Design diagrams (UML, ERD) | Software Architect | 8 | 9 | 1
Phase 3: Implementation
Developing the system | Software Architect / Devs | 9 | 12 | 4
Phase 4: Testing & QA
Prepare a test plan document | Test Engineer | 9 | 10 | 1
Conduct testing with users | Test Engineer | 10 | 12 | 2
Phase 5: Project Closure
Final Report & Presentation | Project Manager / All | 12 | 13 | 1
Final Product Delivery | Project Manager | 13 | 13 | 1